## Build Plan
KAIZORA Agentic Commerce — Build Plan
SUMMARY
| Section | Items | Status Breakdown
| Phase 1 — Foundation | 8 | 2 Partial, 6 Not Built
| Phase 2 — Intelligence | 7 | 1 Partial, 6 Not Built
| Phase 3 — Optimization | 4 | 4 Not Built
| TOTAL | 19 | 3 Partial, 16 Not Built
# | Item | Type | Phase | Status | Description | Dependencies | Connects To
1 | asset_commerce_profiles table | DB Table | Phase 1 | Not Built | Bridge table connecting Decision Layer and Marketplace. Stores commerce scores, suggestions, and readiness data per asset. | None | Decision Layer, all commerce agents
2 | Commerce Profile Builder API | API Route | Phase 1 | Not Built | POST /api/commerce/profile/build — Hydrates profile from Decision Layer if exists, runs intake agent if not. | asset_commerce_profiles table | Decision Layer evaluate API, Intake Agent
3 | Commerce Intake Agent | Agent Logic | Phase 1 | Not Built | Lightweight agent for marketplace-direct users. Generates description, category, tags, license, price band, policy screening. | asset_commerce_profiles table | Commerce Profile Builder API
4 | Decision Layer → Commerce Pipeline | Agent Logic | Phase 1 | Partial | Wires existing DL output (market_fit, quality, originality, monetization paths) into asset_commerce_profiles. DL exists, bridge doesn't. | asset_commerce_profiles table | decision-layer/evaluate API
5 | Listing Draft Generator API | API Route | Phase 1 | Not Built | POST /api/marketplace/listing/draft — Reads commerce profile, auto-generates title, description, tags, category, price suggestion. | Commerce Profile Builder | creator/listings/create
6 | Listing Construction Agent | Agent Logic | Phase 1 | Not Built | AI agent that consumes commerce profile and generates optimized listing metadata (title, subtitle, description, tags, keywords). | Commerce Profile Builder API | Listing Draft Generator API
7 | Marketplace-Direct Upload Flow | UI Page | Phase 1 | Not Built | New upload path for experienced users — skip Decision Layer, fast intake, quick listing. Optional 'run deeper review' button. | Intake Agent, Listing Draft Generator | creator/listings/create
8 | Guided Flow (DL → Auto-Listing) | UI Page | Phase 1 | Partial | After Decision Layer evaluation, auto-populate listing creation with suggested data. DL exists, auto-population doesn't. | DL → Commerce Pipeline, Listing Draft | Decision Layer UI, creator/listings/create
9 | Pricing Agent Enhancements | Agent Logic | Phase 2 | Partial | Extend pricingAgent.ts with price bands, bundle pricing, discount logic, test pricing. Currently only does demand-based adjustment. | asset_commerce_profiles table | lib/agents/pricingAgent.ts
10 | Packaging Agent | Agent Logic | Phase 2 | Not Built | Suggests product shape: single asset, bundle, collection, template pack, themed series. Uses repeatability score and similarity. | asset_commerce_profiles table | Listing Construction Agent
11 | Bundle Suggestion API | API Route | Phase 2 | Not Built | POST /api/marketplace/bundles/suggest — Finds bundle opportunities using asset similarity, tag overlap, repeatability scores. | asset_commerce_profiles, Packaging Agent | creator/listings UI
12 | Bundle/Collection Management UI | UI Page | Phase 2 | Not Built | Creator UI to view suggested bundles, create collections, manage themed series. One-click bundle creation from suggestions. | Bundle Suggestion API | creator/listings
13 | Merchandising Agent | Agent Logic | Phase 2 | Not Built | Decides which assets to feature, group, cross-sell. Recommends stronger thumbnails/previews. Beyond current feature agent. | asset_commerce_profiles table | lib/agents/featureAssetAgent.ts
14 | Search Optimization Agent | Agent Logic | Phase 2 | Not Built | Improves search keywords, tag structure, semantic discoverability, category placement per asset. | asset_commerce_profiles table | Listing Construction Agent
15 | Catalog Strategy Agent | Agent Logic | Phase 2 | Not Built | Works across user's assets. Finds cross-sell opportunities, storefront shaping, collection gaps. | asset_commerce_profiles, Packaging Agent | Merchandising Agent
16 | Post-Launch Optimization Agent | Agent Logic | Phase 3 | Not Built | Watches views, saves, CTR, purchases, low-conversion inventory. Suggests reprice, retitle, rebundle, refresh preview. | asset_commerce_profiles, live listing data | lib/agents/pricingAgent.ts
17 | Listing Optimize API | API Route | Phase 3 | Not Built | POST /api/marketplace/listing/optimize — Reads performance metrics, recommends adjustments, auto-drafts revised metadata. | Post-Launch Optimization Agent | listings table
18 | Listing Analytics Dashboard | UI Page | Phase 3 | Not Built | Creator-facing analytics: views, saves, CTR, conversions per listing. Shows optimization suggestions inline. | Post-Launch Optimization Agent | creator/listings
19 | Auto-Optimization Flows | Agent Logic | Phase 3 | Not Built | Automated relist/reprice/retitle/rebundle flows. Uses ai_controls for SUGGEST vs AUTO modes. | Post-Launch Optimization Agent, ai_controls | All commerce agents